## Hoja1
Task | Planned Action | Planned Outcome | Time Estimate | Target Completion Date | Criterion | note
Planning | Discuss project goals and requirements with stakeholders | success criteria, scenario | 1 week |  | Criterion A: Planning
Planning | Research on previous solution | architecture and technology stack, solution | 2 weeks |  | Criterion A: Planning; Criterion B: Solution Overview | parallel with 6
Requirement Gathering | Gather detailed requirements and expectations | Requirement Use Cases, Requirement List, System flow chart/Data flow diagram,UML Domain Model | 2 weeks |  | Criterion A: Planning | parallel with 6