## Hoja1
Waterfall Methodology
Task | Planned Action | Planned Outcome | Estimated Duration | Completion Date | Criterion | note
Planning | Discuss project goals and requirements with stakeholders | success criteria, scenario idea | 1 week | 01/15/2025 | Criterion A: Planning
Planning | Interview to Discuss project goals and requirements with my uncle | success criteria notes, functional solution notes,scenario notes | 2 hours | 2025-07-01 | Criterion A: Planning
Planning | Draft explaining the scenario | success criteria draft, functional solution draft, scenario draft | 5 hours | 2025-10-01 | Criterion A: Planning
Planning | Meeting with my uncle to Review of the draft for scenario and criteria | success criteria revised, functional solution revised, scenario revised | 30 mn | 2025-12-01 | Criterion A: Planning
Planning | success criteria and scenario refinment | success criteria proposal, functional solution proposal, scenario proposal | 2 hours | 01/14/2025 | Criterion A: Planning
Planning | Meeting with my uncle to validate of the scenario and criteria | success criteria draft validated ,functional solution draft validated, scenario draft validated | 30 mn | 01/15/2025 | Criterion A: Planning
Planning | Research on previous solution | architecture and technology stack, solution (detailed above) | 2 weeks | 01/26/2025 | Criterion A: Planning; Criterion B: Solution Overview | parallel with 5
Planning | Research on internet | architecture and technology stack draft, solution draft | 5 hours | 01/17/2025 | Criterion A: Planning; Criterion B: Solution Overview
Planning | Revision with the CTO of my uncle | advices correction on architecture and technology stack draft, solution draft | 2 hours | 01/22/2025 | Criterion A: Planning; Criterion B: Solution Overview
Planning | Correction on technology (use JAVA instead of Mobile app for now) | architecture and technology stack proposal, solution proposal, success criteria update | 4 hours | 01/25/2025 | Criterion A: Planning; Criterion B: Solution Overview
Planning | Meeting with my uncle and my uncle CTO to validate the solution | architecture and technology stack validated, solution validated, success criteria revised | 1 hour | 01/26/2025 | Criterion A: Planning; Criterion B: Solution Overview
Requirement Gathering | Gather detailed requirements and expectations | Requirement Use Cases, Requirement List, System flow chart/Data flow diagram (detailed above) | 2 weeks | 2025-07-02 | Criterion A: Planning | parallel with 6
Requirement Gathering | Brainstorming with my uncle to discuss requirements and constraint for players interactions | DFD and constraints, scope of interaction, use case | 1 hour | 2025-01-02 | Criterion B: Solution Overview
Requirement Gathering | Brainstorming with my uncle to discussiscuss on Data that must be stored for functional or business needs, review of data privacy needs | DFD, Domain Model ideation. Data we want to keep in DB are defined, Data privacy taken in account in requirement list | 1 hour | 2025-02-02 | Criterion B: Solution Overview
Requirement Gathering | Brainstorming with my uncle to discussiscussion over game limitation, scoring, and selection, use cases in brainstorming with uncle and its CTO | Discussion over game limitation, scoring, and selection, use cases and requirement list | 1 hour | 2025-04-02 | Criterion B: Solution Overview
Requirement Gathering | Meeting with my uncle and its CTO to check Requirement against Success Criteria and solution for MVP Scope | success criteria validated, requirement list validated, use cases validated, solution validated, UML Domain Model validated | 1 hour | 2025-07-02 | Criterion B: Solution Overview | we are late
Test plan | define test plan with client (2 meetings: 1 for defining, 1 for review) | Test Plan (detailed above) | 1 week | 02/15/2025 | Criterion B: Solution Overview
Test Plan | Test Plan Ideation study over the success criteria | Test plan draft: main test | 1 hour | 2025-09-02 | Criterion B: Solution Overview
Test Plan | workshop with my uncle and some users (players) of my family to review Test Plan Reviewed | Test plan improved: detailled test | 3 hours | 2025-10-02 | Criterion B: Solution Overview
Test Plan | Test Plan Refinement | Test plan proposal | 2 hours | 2025-12-02 | Criterion B: Solution Overview
Test Plan Validation | meeting with my uncle and some users (players) of my family to validate the Test Plan | Test plan defined and validated by client | 1 hour | 02/15/2025 | Criterion B: Solution Overview | time recuperated
Design | game views, player selection, and game logic | Sketch-View-Navigation Model, Chesters Logic Algorithm, Tic Tac Toe Logic Algorithm (detailed above) | 2 weeks | 02/27/2025 | Criterion B: Solution Overview
Design | Research about chesters and tic tac toe rules | Chesters Logic Algorithm, Tic Tac Toe Logic Algorithm | 1 day | 02/19/2025
Design | Analysis - Navigation Ideation | Skecth defining only the main views and basic navigation | 1 hour | 02/20/2025 | Criterion B: Solution Overview
Design | Analysis - View Details | Detail Sketch of each views, requirement list actualized, navigation | 3 hour | 02/22/2025 | Criterion B: Solution Overview
Design | Analysis - Define Game Flow | Abstract Game Flow Chart | 1 hour each | 02/23/2025 | Criterion B: Solution Overview
Design | request for validation from user from my family for View and Navigation Model Validation | Sketch, View and Navigation Model Validated by End User samples | 30 mn | 02/24/2025 | Criterion B: Solution Overview
Design | request for validation from my uncle for View and Navigation Model Validation | Sketch, View and Navigation Model Validated by Client | 30 mn | 02/27/2025 | Criterion B: Solution Overview
Design | Design player database and scoring database | Conceptual Database Entity Relation Model | 1 hour | 2025-01-03 | Criterion C: Development
Development | Implement game features, game views, and selection views | Functional game versions (detailed above) | 6 weeks |  | Criterion C: Development
Planning | we initially decided to implement the database as first development, but the CTO of my uncle advises to start with the application model and views to obtain a rapid visual prototype (using a database mockup) to my uncle, to detect early errors or requirement misses. | plan of task actualized, gantt actualized | 30 mn | 03/27/2025 | Criterion B: Solution Overview
Development | Implement domain model in Java | UML Class Model actualized. Model Domain objects implemented in JAVA and functional | 1 day | 2025-06-03 | Criterion C: Development
Development | Implement a database Mockup | A mockup that will acts as a database access is implemented in JAVA to simulate database access in JAVA | 1 hour | 2025-07-03 | Criterion C: Development
Development | Implement inheritance for Db id and debug functionalies in Domain Model | Classes in model domain inherits the DbId class that implements db id and debug functionalities | 1 hour | 2025-08-03 | Criterion C: Development
Development | Implement a Test Mode | java app may be started in normal or unit test mode | 1 hour | 2025-08-03 | Criterion C: Development
Development | Implement a Unit Test | unit test implemented for Model Domain (generated by chatGPT) and DbMockup (manual done) | 2 hour | 2025-08-03 | Criterion C: Development
Development | Implement HomeView (without game logic and without navigation) | HomeView can be visualized | 5 hours | 2025-10-03 | Criterion C: Development
Design, test plan | For design complexity. we deleted the option of deleting user for now and we only show the top 5 players. Accepted by phone call by my uncles | updated requirements list, use cases and test plan
Development | Implement PlayerSelection (without navigation) | PlayerSelectionView can be visualized. Found a third party class to properly show jcombo with objects. We changed Sketch, View and Navigation Model to better UX | 4 hours | 2025-11-03 | Criterion C: Development | Call phone to my uncle CTO to validate the change in the view of PlayerSelection
Development | Implement GameView (without game logic and without navigation) | GameView can be visualized. | 4 hours | 2025-12-03 | Criterion C: Development
Development | Implement ResultView (without game logic and without navigation) | ResultView Can be visualized for null match anf won match | 4 hours | 03/13/2025 | Criterion C: Development
Development | Implement PlayerCreateView and PlayerEditView (without game logic and without navigation) | PlayerCreate and PlayerEditView can be visualized | 3 hours | 03/14/2025 |  | we actualized MockUpDB to add create and edit players and match result submit
Development | Actualize code comments | Code comment revised | 1 hour | 03/14/2025 | Criterion C: Development
Development | Review View Implementation with my uncle and some users (players) of my family: Demo, and feedback | feedback, model refinment, requirement list actualization | 3 hours | 03/15/2025 | Criterion A: Planning; Criterion B: Solution Overview
Development | Revise Doc | Documentation according to client review and features implemented to now: UML Domain Model, UML class Model, Sketch-View and Navigation Model | 1 hour | 03/18/2025 | Criterion C: Development Criterion B: Solution Overview | Note: we change 2 requirements (number of top players shown, and delete player is not anymore in MVP). Validated by client
Development | Create a Status for our App that will manage the players and game ' s selection | Added a AppStatus class with unit test for main flow views (homeview, selectplayerview, gameview,resultview). Other views (PlayerEditView and PlayerCreateView) dont requires it since they dont requires a selection change. See • Navigation and AppStatus | 6 hours | 03/18/2025 | Criterion C: Development Criterion B: Solution Overview
Development | Create a NavigationController to handle the View Flow | NavigationController can be tested via Unit Test | 5 hours | 03/20/2025 | Criterion C: Development Criterion B: Solution Overview
Development | Integrate NavigationController in views | The views are know working the navigation flow | 12 hours | 03/25/2025 | Criterion C: Development | we had to adapt and change a lot the previous navigation controller
Development | Create a BaseView that all Views will inherit for the communs utilities of views | BaseView Implemented and all view inherits from it | 1 hour | 03/27/2025 | Criterion C: Development
Development | Revise Doc | Documentation according to client review and features implemented to now: AppStatus State Machine, UML View Class Model, Sketch-View | 1 hour | 03/27/2025 | Criterion C: Development Criterion B: Solution Overview | Note: we change 2 requirements (number of top players shown, and delete player is not anymore in MVP). Validated by client
Development | Implement Tic Tac Toe Logic | Working Tic Tac Toe Game | 4 hours | 04/27/2025 | Criterion C: Development
Development | Implement the database | Physical Database Entity Relation Model, DBMS installed, database scheme deployed | 1 week |  | Criterion C: Development
Development | Install mysql | sql installed and running | 3 hours | 05/27/2025 | Criterion C: Development
Development | Create physical database model | Physical DB entity model using https://sqldbm.com/ | 3 hours | 05/27/2025 | Criterion C: Development
Development | importing physical database model and some initial data | Script for generating scheme, script for inserting default data, script for selecting the data | 3 hours | 07/27/2025 | Criterion C: Development
Integration | Integration Logic, Database and View | Functional platform Criterio C document | 2 weeks |  | Criterion C: Development
| create the interface and the required sql statement | Using the mockup, we extract its interface to create the db interface, and we created all the required sql statements | 1 hour | 08/27/2025
Testing Phase | Conduct internal and user testing | Conform to Test Plan | 3 weeks |  | Criterion D: Functionality
Final Review | Review the games with stakeholders and clients | Final approval for release | 1 day |  | Criterion E: Evaluation
Release | Launch the games to the public | Games available to users | 1 day |  | Criterion E: Evaluation
Agil Methodology
Task | Planned Action | Planned Outcome | Time Estimate | Target Completion Date | Criterion
Sprint Planning | Plan sprints and define tasks for each sprint | Sprint backlog: stories and discussion about architecture and technology stack, solution | 1 day |  | Criterion A: Planning
Sprint 1: Prototype | Develop initial prototypes for Tic Tac Toe and Checkers | architecture and technology stack, solution, test plan relative to tic tac toe and checkers game, UML Domain Model relative to games, Sketch and Navigation Model relative to game view, Chesters Logic Algorithm, Tic Tac Toe Logic Algorithm => functional tic tac toe and checkers game | 2 weeks |  | Criterion B: Solution Overview, Criterion C: Development
Sprint Review | Review prototypes with stakeholders and gather feedback, refine next sprint | Insights for improvement: stories | 1 day |  | Criterion B: Solution Overview, Criterion D: Functionality
Sprint 2: Development | Implement core game features, game selection, and player selection views | test plan relative to game selection and player selection, UML Domain Model relative to players, Sketch and Navigation Model relative to game selection and player selection views, Database Entity Relation Model for players => functional game selection and user selection | 2 weeks |  | Criterion B: Solution Overview, Criterion C: Development
Sprint Review | Review game versions with stakeholders and gather feedback, refine next spring | Insights for improvement: stories | 1 day |  | Criterion B: Solution Overview, Criterion D: Functionality
Sprint 3: Scoring | Design scoring system | test plan relative to scoring, UML Domain Model relative to players, Sketch and Navigation Model relative to game selection and player selection views, Database Entity Relation Model for scoring => functional game scoring | 2 weeks |  | Criterion B: Solution Overview, Criterion C: Development
Sprint Review | Review database implementation with stakeholders and gather feedback | Insights for final adjustments | 1 day |  | Criterion D: Functionality
Sprint 4: Refinement | Refine game features, fix identified issues, and finalize game logic | Improved game versions | 2 weeks |  | Criterion B: Solution Overview, Criterion C: Development
Sprint Review | Review refined games with stakeholders and gather feedback | Insights for final adjustments | 1 day |  | Criterion D: Functionality
Sprint 5: Finalization | Finalize game features and conduct thorough testing | Bug-free games ready for release | 2 weeks |  | Criterion B: Solution Overview, Criterion C: Development, Criterion D: Functionality, Criterion E: Evaluation
Final Review | Review the games with stakeholders and clients | Final approval for release | 1 day |  | Criterion E: Evaluation
Release | Launch the games to the public | Games available to users | 1 day |  | Criterion E: Evaluation
Spiral Methodology
Task | Planned Action | Planned Outcome | Time Estimate | Target Completion Date | Criterion
Stakeholder Meeting | Discuss project goals and initial requirements | Initial understanding of project scope (scenario, success criterias), updated Requirement Use Cases and List | 2 hours |  | Criterion A: Planning
Risk Analysis | Identify and analyze potential risks | Risk mitigation plan, updated Requirement Use Cases and List | 1 week |  | Criterion A: Planning | parallel with 36
Previous Solution Analysis | Research on previous solution | architecture and technology stack, solution | 1 weeks |  | Criterion A: Planning;Criterion B: Solution Overview | parallel with 35
Prototype Development | Develop initial prototypes for Tic Tac Toe and Checkers | Functional prototypes, updated Design, Conceptual Model, UML Domain Model, Sketch and Navigation Model for only tic tac toe and checkers game and game view | 2 weeks |  | Criterion C: Development
User Feedback | Gather feedback from users on prototypes | Insights for improvement, updated Requirement Use Cases and list | 1 week |  | Criterion D: Functionality
Requirement Refinement | Refine requirements based on feedback | Updated requirement document, updated Requirement List, System Flow Chart/Data Flow Diagram | 1 week |  | Criterion B: Solution Overview
Design Phase | Create detailed design for game views, player selection, and game logic | Functional prototypes, updated Design, Conceptual Model, UML Domain Model, Sketch and Navigation Model for game selection and player selection | 2 weeks |  | Criterion B: Solution Overview
Database Implementation | Design and implement player database and scoring system | Functional player and scoring database, updated Database Entity Relation Model, MySQL Entity Relation Model | 2 weeks |  | Criterion C: Development
Development Phase | Implement game features, game views, and selection views | Functional game versions, updated UML Class Model, UML Vista Class Model, Tic Tac Toe algorithm, Checkers algorithm, Scoring Algorithm | 4 weeks |  | Criterion C: Development
Testing Phase | Conduct internal and user testing | Identified and fixed bugs, updated Test Plan | 2 weeks |  | Criterion D: Functionality
Final Review | Review the games with stakeholders and clients | Final approval for release, updated Test Plan | 1 day |  | Criterion E: Evaluation
Release | Launch the games to the public | Games available to users | 1 day |  | Criterion E: Evaluation