## Hoja1
Waterfall Methodology
Task | Planned Action | Planned Outcome | Time Estimate | Target Completion Date | Criterion | note
Planning | Discuss project goals and requirements with stakeholders | success criteria, scenario | 1 week | 01/15/2025 | Criterion A: Planning
Planning | Research on previous solution | architecture and technology stack, solution | 2 weeks | 01/29/2025 | Criterion A: Planning; Criterion B: Solution Overview | parallel with 6
Requirement Gathering | Gather detailed requirements and expectations | Requirement Use Cases, Requirement List, System flow chart/Data flow diagram,UML Domain Model | 2 weeks | 01/29/2025 | Criterion A: Planning | parallel with 6
Test plan | define test plan with client (2 meetings: 1 for defining, 1 for review) | Test Plan | 1 week | 07/19/2025 | Criterion B: Solution Overview
Design | Create game design, including UI/UX, game views, player selection, and game logic | Sketch and Navigation Model, Chesters Logic Algorithm, Tic Tac Toe Logic Algorithm | 2 weeks | 08/19/2025 | Criterion B: Solution Overview
Design | Design player database and scoring system | Conceptual Database Entity Relation Model | 2 weeks | 2025-05-03 | Criterion C: Development
Development | Implement game features, game views, and selection views | Functional game versions, Criterio C document | 6 weeks | 04/16/2025 | Criterion C: Development
Development | Implement the database | Physical Database Entity Relation Model, Database installed and operative, Database model deployed and accessible | 1 week
Integration | Integration Logic, Database and View | Functional platform Criterio C document | 2 weeks |  | Criterion C: Development
Testing | Conduct internal and user testing | Conform to Test Plan | 3 weeks | 2025-07-05 | Criterion D: Functionality
Review | Review the games with stakeholders and clients | Final approval for release | 1 day | 2025-08-05 | Criterion E: Evaluation
Release | Launch the games to the public | Games available to users | 1 day | 2025-09-05 | Criterion E: Evaluation
Agil+15:36e Methodology
Task | Planned Action | Planned Outcome | Time Estimate | Target Completion Date | Criterion
Sprint Planning | Plan sprints and define tasks for each sprint | Sprint backlog: stories and discussion about architecture and technology stack, solution | 1 day | 01/15/2025 | Criterion A: Planning
Sprint 1: Prototype | Develop initial prototypes for Tic Tac Toe and Checkers | architecture and technology stack, solution, test plan relative to tic tac toe and checkers game, UML Domain Model relative to games, Sketch and Navigation Model relative to game view, Chesters Logic Algorithm, Tic Tac Toe Logic Algorithm => functional tic tac toe and checkers game | 2 weeks | 01/29/2025 | Criterion B: Solution Overview, Criterion C: Development
Sprint Review | Review prototypes with stakeholders and gather feedback, refine next sprint | Insights for improvement: stories | 1 day | 01/30/2025 | Criterion B: Solution Overview, Criterion D: Functionality
Sprint 2: Development | Implement core game features, game selection, and player selection views | test plan relative to game selection and player selection, UML Domain Model relative to players, Sketch and Navigation Model relative to game selection and player selection views, Database Entity Relation Model for players => functional game selection and user selection | 2 weeks | 02/13/2025 | Criterion B: Solution Overview, Criterion C: Development
Sprint Review | Review game versions with stakeholders and gather feedback, refine next spring | Insights for improvement: stories | 1 day | 02/14/2025 | Criterion B: Solution Overview, Criterion D: Functionality
Sprint 3: Scoring | Design scoring system | test plan relative to scoring, UML Domain Model relative to players, Sketch and Navigation Model relative to game selection and player selection views, Database Entity Relation Model for scoring => functional game scoring | 2 weeks | 02/28/2025 | Criterion B: Solution Overview, Criterion C: Development
Sprint Review | Review database implementation with stakeholders and gather feedback | Insights for final adjustments | 1 day | 02/29/2025 | Criterion D: Functionality
Sprint 4: Refinement | Refine game features, fix identified issues, and finalize game logic | Improved game versions | 2 weeks | 03/14/2025 | Criterion B: Solution Overview, Criterion C: Development
Sprint Review | Review refined games with stakeholders and gather feedback | Insights for final adjustments | 1 day | 03/15/2025 | Criterion D: Functionality
Sprint 5: Finalization | Finalize game features and conduct thorough testing | Bug-free games ready for release | 2 weeks | 03/29/2025 | Criterion B: Solution Overview, Criterion C: Development, Criterion D: Functionality, Criterion E: Evaluation
Final Review | Review the games with stakeholders and clients | Final approval for release | 1 day | 03/30/2025 | Criterion E: Evaluation
Release | Launch the games to the public | Games available to users | 1 day | 03/31/2025 | Criterion E: Evaluation
Spiral Methodology Record of Tasks
Task | Planned Action | Planned Outcome | Time Estimate | Target Completion Date | Criterion
Stakeholder Meeting | Discuss project goals and initial requirements | Initial understanding of project scope (scenario, success criterias), updated Requirement Use Cases and List | 2 hours | 01/15/2025 | Criterion A: Planning
Risk Analysis | Identify and analyze potential risks | Risk mitigation plan, updated Requirement Use Cases and List | 1 week | 01/22/2025 | Criterion A: Planning | parallel with 36
Previous Solution Analysis | Research on previous solution | architecture and technology stack, solution | 1 weeks | 01/22/2025 | Criterion A: Planning;Criterion B: Solution Overview | parallel with 35
Prototype Development | Develop initial prototypes for Tic Tac Toe and Checkers | Functional prototypes, updated Design, Conceptual Model, UML Domain Model, Sketch and Navigation Model for only tic tac toe and checkers game and game view | 2 weeks | 2025-05-02 | Criterion C: Development
User Feedback | Gather feedback from users on prototypes | Insights for improvement, updated Requirement Use Cases and list | 1 week | 2025-12-02 | Criterion D: Functionality
Requirement Refinement | Refine requirements based on feedback | Updated requirement document, updated Requirement List, System Flow Chart/Data Flow Diagram | 1 week | 02/19/2025 | Criterion B: Solution Overview
Design Phase | Create detailed design for game views, player selection, and game logic | Functional prototypes, updated Design, Conceptual Model, UML Domain Model, Sketch and Navigation Model for game selection and player selection | 2 weeks | 2025-05-03 | Criterion B: Solution Overview
Database Implementation | Design and implement player database and scoring system | Functional player and scoring database, updated Database Entity Relation Model, MySQL Entity Relation Model | 2 weeks | 03/19/2025 | Criterion C: Development
Development Phase | Implement game features, game views, and selection views | Functional game versions, updated UML Class Model, UML Vista Class Model, Tic Tac Toe algorithm, Checkers algorithm, Scoring Algorithm | 4 weeks | 04/16/2025 | Criterion C: Development
Testing Phase | Conduct internal and user testing | Identified and fixed bugs, updated Test Plan | 2 weeks | 04/30/2025 | Criterion D: Functionality
Final Review | Review the games with stakeholders and clients | Final approval for release, updated Test Plan | 1 day | 2025-01-05 | Criterion E: Evaluation
Release | Launch the games to the public | Games available to users | 1 day | 2025-02-05 | Criterion E: Evaluation