## Hoja1
Task | Planned Action | Planned Outcome | Duration | Completion Date | Criterion | note
Planning | Discuss project goals and requirements with stakeholders | success criteria, scenario (detailed above) | 1 week | 01/15/2025 | Criterion A: Planning
Planning | Interview to Discuss project goals and requirements with my uncle | success criteria notes, functional solution notes,scenario notes | 2 hours | 2025-07-01 | Criterion A: Planning
Planning | Draft explaining the scenario | success criteria draft, functional solution draft, scenario draft | 5 hours | 2025-10-01 | Criterion A: Planning
Planning | Meeting with my uncle to Review of the draft for scenario and criteria | success criteria revised, functional solution revised, scenario revised | 30 mn | 2025-12-01 | Criterion A: Planning
Planning | success criteria and scenario refinment | success criteria proposal, functional solution proposal, scenario proposal | 2 hours | 01/14/2025 | Criterion A: Planning
Planning | Meeting with my uncle to validate of the scenario and criteria | success criteria draft validated ,functional solution draft validated, scenario draft validated | 30 mn | 01/15/2025 | Criterion A: Planning
Planning | Research on previous solution | architecture and technology stack, solution (detailed above) | 2 weeks | 01/26/2025 | Criterion A: Planning; Criterion B: Solution Overview | parallel with 5
Planning | Research on internet | architecture and technology stack draft, solution draft | 5 hours | 01/17/2025 | Criterion A: Planning; Criterion B: Solution Overview
Planning | Revision with the CTO of my uncle | advices correction on architecture and technology stack draft, solution draft | 2 hours | 01/22/2025 | Criterion A: Planning; Criterion B: Solution Overview
Planning | Correction on technology (use JAVA instead of Mobile app for now) | architecture and technology stack proposal, solution proposal, success criteria update | 4 hours | 01/25/2025 | Criterion A: Planning; Criterion B: Solution Overview
Planning | Meeting with my uncle and my uncle CTO to validate the solution | architecture and technology stack validated, solution validated, success criteria revised | 1 hour | 01/26/2025 | Criterion A: Planning; Criterion B: Solution Overview